## Ark1
Sprint backlog
Dato for start | User Storries | To do | In Progress | To Verify | Done | Participants
2015-03-30 | Database |  |  | all Tables | almost all tables called done 9-4-15, but need further redoing | Dennis Ebbe Christoffer Andreas Rune
2015-04-02 | Opret kampagneforespørgelse | tranfer MDF DTO to DB | Tranfer MDF DTO to DB | all |  | Dennis Ebbe Christoffer Andreas Rune
2015-04-09 | Se igangværende kampagner | JSP siden servlet queries UUID unik id til at finde kampagne igen | JSP siden servlet queries UUID unik id | all |  | Rune(queries, DB UUID) Christoffer(queries, DB, UUID) Ebbe(er du okay) Andreas(JSP)
2015-04-08 | Upload POE data | JSP siden servlet queries DB script billedfiler | JSP siden servlet queries UUID til POE Fil upload(DBscript) |  | DB ID_MDF DB ID_POE DB ID sequence | Rune(queries, DB UUID) Christoffer(queries, DB, UUID) Ebbe(er du okay) Andreas(JSP) Dennis (JSP)